## Sheet1
Goal | Description | Deliverable | Risks | Timeline | Proposed new timeline | Progress | Notes
COMPUTE.1 | Finalise short term plan | Plan produced and agreed by Strategy Committee | Availability of effort to produce and agree plan | Complete by April 2022 |  | 100 | Agreed using EIDF. SRRG formed. Funding for server room expansion obtained
COMPUTE.2 | Implement short term plan | Actions complete | Unknown at this stage | Complete by June 2022 |  | 100
COMPUTE.3 | Produce long term plan | Plan produced and agreed by Strategy Committee | Availability of effort to produce and agree plan | Complete by Autumn 2022 |  | 100 | Overtaken by events?
COMPUTE.4 | Implement long term plan | Actions complete | Unknown at this stage | Unknown at this stage | Autumn 2023 | 75 | Awaiting EIDF and Forum server room cooling expansion
COMPUTE.5 | Develop procurement framework | A framework, akin to the Select Server contract, for purchasing GPU servers | Dependency on UoE Procurement | Complete by December 2022 | Autumn 2023 | 0 | Central procurement too busy, plus no capacity for additional servers
COMPUTE.6 | Consider external consultant's recommendations and act appropriately | Plan for implementing recommendations | Dependency on Estates and funding | Complete by Summer 2022 | Autumn 2023 | 50 | Work now funded. Design consultant and QS appointed. Detailed surveys by end of Jan. Expected completion Sept 2023
EDLAN.1 | Evaluate management models | Produce a report for Strategy | Insufficient information from CIS, project delayed until after possible School staff retirements | Ideally by April 2022, but subject to CIS014 project scheduling | Completed by April 2023 | 75 | No report, still pending prototyping - held up by lack of test framework in new EdLAN and engagement from CIS.
EDLAN.2 | Identify changes required | Prototypes and implementation plan | Insufficient information from CIS, project delayed until after possible School staff retirements | Ideally by May 2022, but subject to CIS014 project scheduling | Completed by April 2023 | 50 | as above
EDLAN.3 | Implement changes required | Add required support to infrastructure | Insufficient information from CIS, project delayed until after possible School staff retirements | Ideally by July 2022, but subject to CIS014 project scheduling | Completed by June 2023 | 50 | Using new EdLAN distribution at all sites.
EDLAN.4 | Rollout new EdLAN across School | School entirely on new EdLAN |  | Unknown at this stage | Completed by Autumn 2023 | 0
DATAMANAGE.1 | Produce data asset register | Completion of relevent development projects. | Maintenance of register depends on input by academic staff. Project for maintenance of register needs to be resourced. | Initial implementation complete. Integration with school systems and datarefresh ongoing. Complete by July 2022 | Completed by April 2023 | 75 | Delayed by necessary feature creep, but now drawing a line.
DATAMANAGE.2 | Produce School DMP policy | Policy agreed to by relevant School committee | Requires agreement by committee | Completed? |  | ??? | who owns this now?
DATAMANAGE.3 | Complete work to separate backup streams | Implementation of facility for separate management streams. Identification of relevent data. | Identification of relevent data depends on DATAMANAGE.1 | Documentation and policy still to complete. Complete by April 2022 |  | 100
DATAMANAGE.4 | Produce Use Case guidance | Produce number of 'user stories' covering different aspects of research data requirements | Availability of academic and School and University research data staff effort to identify and produce suitable case studies. | Complete by June 2022 |  | 100
DATAMANAGE.5 | Improve staff understanding of data security best practice | Produce a course on implications of not following best practice data security | Availability of course preparation tools in P&M | Complete by August 2022 |  |  | University guidance has improved such that we will point users at this instead
SEP.2 | Identify and implement - Procurement | Unknown at this stage | Information not forthcoming before go-live | Complete by end 2022? | Complete by summer 2023 | 75 | Still need to decide on whether to let academics loose on system
SEP.3 | Identify and implement - Finance | Unknown at this stage | Risk that will need to revert to manual entry, information not forthcoming before go-live | Complete by end 2022? |  |  | All required work covered by SEP.4
SEP.4 | Identify and implement - Guaranteed Hours | Unknown at this stage | Unknown at this stage | Complete by end 2022? | Complete by summer 2023 | 25 | 22/23 teaching support contracts and payroll complete. Approach for 23/24 to be decided and implemented
FLEXIBLEWORKING.1 | Placemarker
FLEXIBLEWORKING.1 | Placemarker
FLEXIBLEWORKING.1 | Placemarker
FLEXIBLEWORKING.1 | Placemarker
FLEXIBLEWORKING.1 | Placemarker
STREAMLINING.1 | Review current activities | Options paper for discussion at CSG |  | Complete by March 2022 | Complete by March 2023 | 75 | Discussed at CEG and actions produced
STREAMLINING.2 | Discuss options paper at CSG | Agreed approach |  | Complete by May 2022 | Complete by March 2023 | 0
STREAMLINING.3 | Produce implementation plan | Implementation plan |  | Complete by July 2022 | Complete by May 2023 | 0
STREAMLINING.4 | Implement plan | Released effort |  | Complete by end 2022? | Complete by summer 2023 | 0
STREAMLINING.5 | Restructure Theon into suite of micro services | Multiple micro services, decommissioning of Theon portal | Increased fragility of service if not completed | Complete by May 2023 | Complete by Autumn 2023 | 25 | Some work already started
WEBSTRATEGY.1 | Complete audit of current web estate | Database of web estate | None identified | Complete by March 2022 | Complete by May 2023 | 75 | Still to audit groups.inf.ed.ac.uk
WEBSTRATEGY.2 | Produce SWOT analysis of current web estate | Marked up database of web estate | None identified | Complete by June 2022 | Complete by June 2023 | 75
WEBSTRATEGY.3 | Produce agreed web strategy | Agreed strategy document | None identified | Complete by September 2022 | Complete by Autumn 2023 | 75 | Producing draft web strategy in early 2023.
SECURITY.1 | Implement IA recommendations | Produce action plan for implementation | None identified | Complete by May 2022 | Complete by March 2023 | 25 | Have reviewed IS data security standards and evaluated ourselves against those standards - report to be completed
SECURITY.2 | Reassess threat model | Produce discussed report | None identified | Complete by June 2022 | Complete by June 2023 | 0 | Insufficient effort
SECURITY.3 | Develop plan for improving resilience | Produce agreed plan | None identified | Complete by end 2022 | Complete by June 2023 | 0 | Insufficient effort
SECURITY.4 | Implement low hanging fruit | Implementation of low hanging items identified | None identified | Complete by end 2023 | Complete by end 2023 | 25 | Increased segmentation, removed homepages for students, nsu obsoleted
SECURITY.5 | Implement plan | Implementation of big ticket items and also a structure for keeping on top of things going forward | Availability of School academic, research and PS staff effort | Complete by end 2023 | Complete by end 2023 | 0
DICESERVER.1 | Confirm Ubuntu meets needs |  |  | Complete by March 2022 |  | 100
DICESERVER.2 | Develop LCFG managed DICE server platform |  |  | Complete by July 2022 |  | 100
DICESERVER.3 | Port all existing LCFG components |  |  | Complete by December 2022 | Complete by summer 2023 | 75
DICESERVER.4 | Upgrade all DICE servers |  | Insufficient effort to upgrade all servers by SL7 EOL date 30/06/24 | Complete by December 2023 | Complete by summer 2023 | 25
Theme | Activity | Progress | Notes
Security | Convert all web sites from HTTP to HTTPS | 75 | (Actually 95% complete)
Services | Review whether the existing network file system is still appropriate for School’s requirements and identify possible alternatives | 0
Services | Review current school use of Sharepoint and produce a strategy for future use | 25 | Discussions underway
Facilities | Update the AV facilities in the Informatics Forum - and adapt for hybrid meetings and seminars | 75 | MF2, 5.02, IMR remain
Teaching | Reduce the number of submissions systems to the minimum required | 75 | Evaluating GitHub Education
Admin | Review PGR application scraper code, improve and document as required | 50 | Code reviewed and understood. Currently discussing potential improvements
Admin | Refactor Theon database into multiple micro databases to improve maintainability and GDPR compliance. (Added May 2022) | Duplicate of STREAMLINING.5 | n/a
Sustainability | Improve recharging of computing staff time to research grants | 75 | Developed an agreed plan. Now to implement.
Sustainability | Succession planning | 100 | Will be ongoing